## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Fetch historical daily data for at least 2 cryptocurrencies from a free API. | MUST HAVE | None | Gowtham | 3- Completed
Sprint 1 | Sprint 1 | US-002 | Extend the data fetching to cover all 6 cryptocurrencies (BTC, ETH, SOL, etc.). | COULD HAVE | US-001 | Gowtham | 3- Completed
Sprint 1 | Sprint 1 | US-003 | Store the fetched raw data in a local SQLite database (crypto_prices table). | MUST HAVE | US-001 | Gowtham | 3- Completed
Sprint 1 | Sprint 1 | US-004 | Apply parallel tasks concepts to the data fetching and storage steps. | SHOULD HAVE | US-001 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-005 | Implement portfolio weighting rules based on the "1st September" slide (Portfolio_math.py). | MUST HAVE | US-003 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-006 | Calculate the portfolio return and risk for each strategy. | MUST HAVE | US-005 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-007 | Create two new tables (portfolio, portfolio_assets) to store calculated metrics (returns, risk, weights). | MUST HAVE | US-006 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-008 | Extend the parallel logic to run all rule tests at the same time using a ThreadPool. | SHOULD HAVE | US-006 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-009 | Compare the historical return of a portfolio vs. a single asset and plot the results on a graph. | MUST HAVE | US-007 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-010 | Draw data-driven insights from the comparison and export the final report data to a CSV file. | SHOULD HAVE | US-009 | Gowtham | 3- Completed
Sprint 2 | Sprint 2 | US-011 | Create a README.md file that documents all the work done in Milestone 2. | MUST HAVE | US-005, US-009 | Gowtham | 3- Completed
Sprint 3 | Sprint 3 | US-012 | Implement the 6 advanced risk rules from the "Sep 16th" slide (Risk_checker.py). | MUST HAVE | US-006 | Gowtham | 3- Completed
Sprint 3 | Sprint 3 | US-013 | Store the PASS/FAIL results of the risk checks in the database. | MUST HAVE | US-012 | Gowtham | 3- Completed
Sprint 3 | Sprint 3 | US-014 | Send an email alert if any of the risk rules fail. | SHOULD HAVE | US-012 | Gowtham | 3- Completed
Sprint 3 | Sprint 3 | US-015 | Build and train a Linear Regression model to predict returns for coins and portfolios (predictor.py). | COULD HAVE | US-012 | Gowtham | 3- Completed
Sprint 4 | Sprint 4 | US-016 | Implement atleast 1 dynamic investment spreading rules (Equal, Risk-Parity, Sharpe-Max, Momentum). | MUST HAVE | US-002 | Gowtham | 3- Completed
Sprint 4 | Sprint 4 | US-017 | Implement the 4 new dynamic investment spreading rules (Equal, Risk-Parity, Sharpe-Max, Momentum). | SHOULD HAVE | US-002 | Gowtham | 3- Completed
Sprint 4 | Sprint 4 | US-018 | Create a stress test framework using the 3 sample market scenarios (Bull, Bear, Volatile). | MUST HAVE | US-016, US-017 | Gowtham | 3- Completed
Sprint 4 | Sprint 4 | US-019 | Analyze and generate a final summary report comparing the performance of each rule in each scenario. | SHOULD HAVE | US-018 | Gowtham | 3- Completed
Sprint 4 | Sprint 4 | US-020 | Prepare a final presentation script to clearly explain the stress test results and conclusions. | SHOULD HAVE | US-019 | Gowtham | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
[8 empty] | 93 | 5 | 3 | 6 | 4 | 6 | 3 | 4 | 3 | 4 | 2 | 2 | 8 | 4 | 5 | 6 | 4 | 8 | 7 | 5 | 4
SPRINT 1 (14-Aug to 27-Aug) | bar: Day 1 to Day 14
US-001 | T-001 | Develop function to fetch data for at least 2 coins. | 2025-08-14 | 2025-08-14 | Gowtham | Development | Done | 5 | Day 1: 5
US-002 | T-002 | Extend fetching logic to support all 6 coins. | 2025-08-18 | 2025-08-19 | Gowtham | Development | Done | 3 | Day 2: 3
US-003 | T-003 | Implement SQLite connection and create crypto_prices table. | 2025-08-20 | 2025-08-22 | Gowtham | Database | Done | 6 | Day 3: 6
US-004 | T-004 | Refactor data fetching to use ThreadPoolExecutor. | 2025-08-25 | 2025-08-26 | Gowtham | Development | Done | 4 | Day 4: 4
SPRINT 2 (28-Aug to 10-Sep) | bar: Day 1 to Day 14
US-005 | T-005 | Implement assign_weights function with all 5 rules and 40% constraint. | 2025-08-28 | 2025-09-01 | Gowtham | Development | Done | 6 | Day 5: 6
US-006 | T-006 | Implement functions to calculate portfolio return and risk. | 2025-09-02 | 2025-09-02 | Gowtham | Development | Done | 3 | Day 6: 3
US-007 | T-007 | Create portfolio and portfolio_assets tables and store metrics. | 2025-09-03 | 2025-09-04 | Gowtham | Database | Done | 4 | Day 7: 4
US-008 | T-008 | Refactor analysis to run all rule tests in parallel. | 2025-09-05 | 2025-09-05 | Gowtham | Development | Done | 3 | Day 8: 3
US-009 | T-009 | Develop logic to compare portfolio vs. single asset and plot graphs. | 2025-09-08 | 2025-09-09 | Gowtham | Development | Done | 4 | Day 9: 4
US-010 | T-010 | Implement CSV export for the final report. | 2025-09-10 | 2025-09-10 | Gowtham | Development | Done | 2 | Day 10: 2
US-011 | T-011 | Write the README.md file. | 2025-09-10 | 2025-09-10 | Gowtham | Documentation | Done | 2 | Day 11: 2
SPRINT 3 (11-Sep to 24-Sep) | bar: Day 1 to Day 14
US-012 | T-012 | Implement the 6 advanced risk rule functions (Sharpe, Beta, etc.). | 2025-09-11 | 2025-09-15 | Gowtham | Development | Done | 8 | Day 12: 8
US-013 | T-013 | Refactor the data fetching logic to use concurrent.futures.ThreadPoolExecutor. | 2025-08-29 | 2025-09-01 | Gowtham | Development | Done | 4 | Day 13: 4
US-014 | T-014 | Refactor the portfolio analysis logic to run each rule test in parallel. | 2025-09-02 | 2025-09-02 | Gowtham | Development | Done | 5 | Day 14: 5
US-015 | T-015 | Implement the functions for Sharpe Ratio, Max Drawdown, and Sortino Ratio. | 2025-09-03 | 2025-09-04 | Gowtham | Development | Done | 6 | Day 15: 6
SPRINT 4 (29-Sep to 14-Oct) | bar: Day 1 to Day 14
US-016 | T-016.1 | Implement the 'Equal-Weight' rule in the assign_weights function. | 2025-09-29 | 2025-09-29 | Gowtham | Development | Done | 1 | bar: Day 16
US-016 | T-016.2 | Implement the dynamic 'Risk-Parity' rule, including volatility calculation. | 2025-09-29 | 2025-09-29 | Gowtham | Development | Done | 3 | Day 16: 3
US-016 | T-016.3 | Implement the dynamic 'Sharpe-Maximization' rule, handling negative Sharpe ratios. | 2025-09-30 | 2025-09-30 | Gowtham | Development | Done | 4 | Day 17: 4
US-016 | T-016.4 | Implement the dynamic 'Momentum' rule, handling negative total returns. | 2025-09-30 | 2025-09-30 | Gowtham | Development | Done | 4 | Day 17: 4
US-017 | T-017.1 | Create the 3 sample Pandas DataFrames for the Bull, Bear, and Volatile market scenarios. | 2025-10-01 | 2025-10-01 | Gowtham | Data Science | Done | 2 | Day 18: 2
US-017 | T-017.2 | Develop the main script loop to iterate through each scenario and apply each of the 4 rules. | 2025-10-01 | 2025-10-01 | Gowtham | Development | Done | 5 | Day 18: 5
US-018 | T-018.1 | Write the logic to calculate the Total_Return and Volatility for each test run. | 2025-10-02 | 2025-10-02 | Gowtham | Development | Done | 3 | Day 19: 3
US-018 | T-018.2 | Aggregate all results into a final Pandas DataFrame to create the summary table. | 2025-10-02 | 2025-10-02 | Gowtham | Development | Done | 2 | Day 19: 2
US-019 | T-019.1 | Analyze the final summary table and write down the key data-driven insights and conclusions. | 2025-10-03 | 2025-10-03 | Gowtham | Documentation | Done | 2 | Day 20: 2
US-019 | T-019.2 | Structure the insights into a clear, step-by-step presentation script for the final review. | 2025-10-03 | 2025-10-03 | Gowtham | Presentation | Done | 2 | Day 20: 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on X3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on Y3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on Z3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on AA3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on AB3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work
Note on AC3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 1 (14-Aug) | Startup Meeting: Project kickoff and Sprint 1 planning. | Confirmed goals for Sprint 1: establish a robust data pipeline.
1 | Day 2 (15-Aug) | Daily Scrum: Discussed progress. Impediment: Initial API choice (Binance) is geo-blocked (451 Error), halting progress. | Action: Researched and switched the data source to the globally accessible KuCoin API.
1 | Day 3 (18-Aug) | Daily Scrum: Progress update on API integration. No new impediments. | Continued development on the data fetching and processing functions.
1 | Day 4 (19-Aug) | Daily Scrum: Update on database schema. No new impediments. | Continued development on the database creation and data insertion logic.
1 | Day 5 (20-Aug) | Daily Scrum: Progress on portfolio rules. No new impediments. | Began implementation of the assign_weights function.
1 | Day 6 (21-Aug) | Daily Scrum: Discussed weighting logic. No new impediments. | Continued development on the portfolio weighting rules.
1 | Day 7 (22-Aug) | Daily Scrum: Update on constraints. No new impediments. | Completed the assign_weights function, including the 40% constraint.
1 | Day 8 (25-Aug) | Daily Scrum: Final review of Sprint 1 tasks. No new impediments. | Started implementation of the calculate_portfolio_return function.
1 | Day 9 (26-Aug) | Daily Scrum: Sprint 1 nearing completion. No new impediments. | Completed all remaining Sprint 1 development tasks.
1 | Day 10 (27-Aug) | Sprint Review: Presented the working data pipeline and analysis engine. | Confirmed all Sprint 1 User Stories are complete and ready for the next phase.
2 | Day 1 (28-Aug) | Startup Meeting: Project check-in and Sprint 2 planning. | Confirmed goals for Sprint 2: parallelize logic and build the reporting module.
2 | Day 2 (29-Aug) | Daily Scrum: Progress update. No new impediments. | Continued development on database storage for portfolio metrics.
2 | Day 3 (01-Sep) | Daily Scrum: Discussed parallel processing design. Impediment: Initial attempt at parallel DB writes caused database is locked error. | Redesigned the parallel logic. Threads will now only perform calculations and return results; the main thread will perform the single, safe database write.
2 | Day 4 (02-Sep) | Daily Scrum: Update on refactoring. No new impediments. | Implemented the corrected parallel processing logic.
2 | Day 5 (03-Sep) | Daily Scrum: Progress on reporting. No new impediments. | Started development on the portfolio vs. single asset comparison function.
2 | Day 6 (04-Sep) | Daily Scrum: Update on plotting. No new impediments. | Continued development on the matplotlib visualization.
2 | Day 7 (05-Sep) | Daily Scrum: Reporting module nearing completion. No new impediments. | Completed the plotting and insights generation.
2 | Day 8 (08-Sep) | Daily Scrum: Update on CSV export. No new impediments. | Implemented the final CSV export functionality.
2 | Day 9 (09-Sep) | Daily Scrum: Progress on documentation. No new impediments. | Started writing the README.md file.
2 | Day 10 (10-Sep) | Sprint Review: Presented the parallelized pipeline and the final visual report. | Confirmed all Sprint 2 User Stories are complete.
3 | Day 1 (11-Sep) | Startup Meeting: Project check-in and Sprint 3 planning. | Confirmed goals for Sprint 3: implement the risk checker and the predictive model.
3 | Day 2 (12-Sep) | Daily Scrum: Progress on risk rule implementation. No new impediments. | Continued development on the advanced risk metric functions.
3 | Day 3 (15-Sep) | Daily Scrum: Risk functions complete. No new impediments. | Completed all 6 risk rule functions.
3 | Day 4 (16-Sep) | Daily Scrum: Progress on database storage for risk results. No new impediments. | Developed the risk_assessment table and the logic to store PASS/FAIL results.
3 | Day 5 (17-Sep) | Daily Scrum: Discussed email alert system. Impediment: SMTP authentication is failing with the standard password (535 Error). | Researched Google's security policy. Enabled 2-Step Verification and generated a 16-digit App Password for secure authentication.
3 | Day 6 (18-Sep) | Daily Scrum: Update on email integration. No new impediments. | Implemented the use of Colab Secrets to securely handle the new App Password.
3 | Day 7 (19-Sep) | Daily Scrum: Risk checker complete. No new impediments. | Completed and tested the full risk checking and alerting workflow.
3 | Day 8 (22-Sep) | Daily Scrum: Progress on predictive model. No new impediments. | Implemented feature engineering and the train/test split for the Linear Regression model.
3 | Day 9 (23-Sep) | Daily Scrum: Update on model training. No new impediments. | Successfully trained the model and generated initial evaluation metrics.
3 | Day 10 (24-Sep) | Final Project Review: Presented the complete, end-to-end pipeline, including the risk checker and predictive model. | Confirmed all Sprint 3 User Stories and the entire project are complete.
4 | Day 1 (25-Sep) | Startup Meeting: Kickoff for the final milestone (Sprint 4). | Implement the 4 new dynamic portfolio rules, run the stress test, and prepare the final presentation materials. No initial impediments identified.
4 | Day 2 (26-Sep) | Daily Scrum: Progress on implementing the new rules. Impediment: The sharpe_max and momentum rules are failing in the "Bear Market" scenario, returning NaN weights because all returns are negative. | Modified the logic for these two rules to use .clip(lower=0). This ensures that assets with negative performance are correctly assigned a weight of zero, resolving the bug.
4 | Day 3 (27-Sep) | Daily Scrum: The Bear Market bug is fixed. Impediment: The risk_parity rule is returning the same weights as equal in the Bull Market test. The result is confusing. | Investigated the data. Confirmed the logic is correct. The small, uniform returns in the sample data caused the volatilities to be nearly identical, leading to the similar weights. Documented this insight for the presentation.
4 | Day 4 (30-Sep) | Daily Scrum: All rules are now working and understood. No new impediments. | Focused on aggregating all results into the final summary table and writing the key insights for the presentation.
4 | Day 5 (01-Oct) | Final Project Review / Presentation: All tasks for Milestone 4 are complete. No impediments. | Presented the final stress test results, explaining the performance of each rule in each market scenario. Submitted all project artifacts and documentation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 (Week 1) | 2025-08-14 | 2025-08-20 | Gowtham | Validating external dependencies (like APIs) on the first day of the sprint to identify major blockers early. | Assuming the primary data source will work without issue, which led to an immediate roadblock. | Writing modular, single-purpose functions from the start, which made it easy to replace the data source later. | Pivoted quickly from the blocked Binance API to the KuCoin API, which resolved the critical 451 error and kept the project on schedule.
2 | 1 (Week 2) | 21-Aug-2025 | 27-Aug-2025 | Gowtham | Creating small, reusable helper functions for common tasks like data validation and cleaning. | Making assumptions about data formats between different libraries (Pandas vs. Python lists), which caused logical errors. | Building a solid database schema with UNIQUE constraints to ensure data integrity from the beginning. | Refactored the portfolio weighting logic to handle floating-point precision issues and ensure weights always sum to exactly 1.
3 | 2 (Week 3) | 28-Aug-2025 | 03-Sep-2025 | Gowtham | Adopting a 'gather-then-write' pattern for any parallel task that interacts with a single resource like a database file. | Trying to write to the SQLite database from multiple threads at once, which resulted in database is locked errors. | Breaking down complex milestones into smaller, clearly defined user stories, which kept the sprint focused. | Rewrote the parallel analysis logic so that worker threads only perform calculations and return results, while the main thread handles the single, safe database write.
4 | 2 (Week 4) | 2025-09-04 | 2025-09-10 | Gowtham | Maintaining a consistent naming convention for all functions and variables to improve code readability and prevent errors. | Allowing minor inconsistencies in function names (calculate_volatility vs. calculate_portfolio_volatility), which led to a NameError. | Integrating components incrementally and testing them together at each stage, which helped identify bugs early. | Performed a code refactor to standardize all function names across the entire project, making the codebase more maintainable.
5 | 3 (Week 5) | 2025-09-11 | 2025-09-17 | Gowtham | Using secure methods like Colab Secrets for all sensitive credentials (passwords, API keys) from the very start of a new feature. | Temporarily hardcoding credentials during development, which is a security risk and caused authentication failures with modern email services. | Thoroughly testing each of the 6 risk rules with both expected PASS and FAIL conditions to ensure the logic was robust. | Implemented the use of a Google App Password stored in Colab Secrets, which fixed the SMTP AuthenticationError and made the alerting system work.
6 | 3 (Week 6) | 2025-09-18 | 2025-09-24 | Gowtham | Clearly documenting the interpretation and limitations of machine learning models as a core part of the final deliverable. | Assuming that a more complex model will automatically lead to better predictive accuracy on noisy financial data. | Creating a single, unified script/notebook that runs the entire end-to-end pipeline, making the project easily reproducible. | Added a detailed conclusion section to the final report that correctly frames the Linear Regression model as a successful baseline and explains why the R-squared is low.
7 | 4 (Week 7) | 2025-09-25 | 2025-10-01 | Gowtham | Creating specific test cases for edge conditions (like a bear market) before writing the main logic. | Assuming a rule that works in one scenario will work in all scenarios, which led to the NaN bug in the stress test. | Using small, simple sample data (the stress test scenarios) to quickly validate complex logic before applying it to the full dataset. | Implemented .clip(lower=0) in the sharpe_max and momentum rules to gracefully handle bear market conditions where all returns are negative.
8 | 4 (Week 8) | 2025-10-02 | 2025-10-08 | Gowtham | Structuring the final presentation as a clear story that explains the "why" behind technical decisions, not just the "what". | Presenting raw output without a clear narrative, which can be confusing for the audience. | Preparing a complete submission package including the final script, a README.md, and all generated artifacts (.db and .csv files). | Created a step-by-step presentation script that explains the stress test results in a simple, insightful way, making the final conclusion clear and impactful.