## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Gowtham | 2025-08-28 | The initial dataset of ~500 rows is insufficient for meaningful analysis. The data pipeline needs to fetch a larger, historical dataset. | 2 | Gowtham | Logical | Modified the KuCoin API call in the data fetching function to include a startAt timestamp, requesting thousands of days of historical data. | 28-Aug-2025 | Closed | The dataset size was successfully increased from ~500 to ~9000 rows, enabling more robust analysis and modeling.
2 | Gowtham | 2025-09-11 | The portfolio rules are assigning more than 50% weight to a single asset, which violates the new diversification constraint. | 3 | Gowtham | Logical | Refactored the assign_weights function to cap any overweight asset at the specified limit (40%) and proportionally redistribute the excess weight to the other assets. | 2025-08-22 | Closed | All portfolio strategies now adhere to the maximum weight constraint, improving the diversification logic.
3 | Gowtham | 2025-09-11 | The final report chart only compares one portfolio vs. one coin. It should compare one portfolio vs. ALL individual coins for a more comprehensive analysis. | 3 | Gowtham | User Interface | Modified the plotting logic in the generate_final_report function to loop through all individual coin symbols and plot each one on the same graph as the main portfolio. | 2025-09-12 | Closed | The final visualization is now much more insightful, providing a full comparison as requested. The user interface (the plot) is more effective.
4 | Gowtham | 2025-09-25 | The evaluation for the predictive model is incomplete. It needs to include a full suite of metrics (MAE, MAPE, R²) and also normalized metrics. | 3 | Gowtham | Standards | Updated the LSTM evaluation function to calculate and print Mean Absolute Error, Mean Absolute Percentage Error, and R-squared. Also added calculations for MSE/RMSE on the scaled data. | 2025-09-25 | Closed | The model evaluation is now comprehensive and follows data science best practices and standards.
5 | Gowtham | 2025-09-25 | The Agile project management documents need to be updated to reflect the full scope of work completed. | 3 | Gowtham | Standards | Filled out all project management documents (Backlog, Sprint Plan, Retrospective, Defect Log) to create a complete and professional record of the project lifecycle. | 2025-09-26 | Closed | The project now meets documentation standards, making it easy to understand and maintain.
6 | Gowtham | 2025-09-26 | The sharpe_max and momentum rules fail in the Bear Market scenario, returning NaN weights. | 4 | Gowtham | Logical | Added a .clip(lower=0) step to the calculations. This ensures that assets with negative performance metrics are correctly assigned a weight of zero. | 2025-09-26 | Closed | The rules are now robust and can handle all market conditions, including all-negative returns. This makes the stress test reliable.
7 | Gowtham | 2025-09-27 | In the Bull Market scenario, the risk_parity rule produces the same weights as the equal rule, which is unexpected. | 4 | Gowtham | Logical | Investigated the sample data. Confirmed the code is correct. The uniform returns in the sample data caused volatilities to be nearly identical. | 2025-09-27 | Closed | The insight was added to the final presentation script to explain the result. No code change was necessary, but the understanding was critical.
8 | Gowtham | 2025-10-02 | Final project documentation (Agile sheets, README.md) is not fully updated to reflect the work from the final sprint. | 4 | Gowtham | Standards | Reviewed and updated all project documents to include all tasks, findings, and deliverables from the final milestone. | 2025-10-02 | Closed | The project now meets documentation standards, making it ready for final submission.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others